## Introduction
Generic Hazard Log
NOTES:
This document presents a generic hazard log compliant both with EN50126-2:2007 and CSM-RA.
Workbook contents:
Introduction | This worksheet
Cover | Cover for the Hazard Log
Hazard Log | The generic hazard log table. See below for content explanation.
SRAC | Table to register the identified additional safety requirements of measures, i.e. the Safety-Related Application Conditions (SRACs). See below for content explanation.
Dashboard | Heat map of risk before and after the introduction of additional safety requirements or measures.
Configuration | Configuration of lists and risk matrix.
Hazard Log contents
Hazard identifier | A unique identifier for the hazard. The identifier should not be changed or reused.
Hazard title | A short description of the hazard, which is meaningful enough to convey the essential nature of the hazard to the reader.
Hazard description | A longer description of the hazard, which is sufficiently precise that one could take any potential state of the system and its environment and say whether the hazard was exhibited or not.
Hazard consequence | The ultimate accident consequences of the hazard. It is important to also document the critical events that will result in the escalation of the hazard consequences, as safety requirements to minimise the rate of occurrence of these events might be necessary (as well as mitigation of accident consequences).
Hazard cause(s) | Each hazard might have a number of different causes. Many safety requirements would map to the hazard at the causal level.
Origin | The activity that resulted in the identification of the hazard.
Existing safety measures | A list, possibly empty, of existing safety measures that act to control the risk associated with this hazard.
Broadly acceptable | ‘Yes’ or ‘No’. Where the answer is yes, a justification of the reasons for the decision.
Likelihood of happening | One of Frequent or almost certain; Likely; Possible; Unlikely; or Rare.
Consequence | One of Insignificant; Minor; Moderate; Major; Catastrophic.
Risk ranking | The overall results of ranking the hazard. The ranking is calculated automatically.
State | An indication of the state of the hazard towards closure. One of open, controlled, cancelled, closed or transferred.
Risk evaluation principle(s) | The risk acceptance principle or principles being used to accept the hazard. It might be that principles need to be associated to specific causes. One of Codes of Practice, Reference System, or Explicit estimation
Risk evaluation documents | References to any documents containing further information about the risk evaluation of this hazard.
Additional safety measure | Details of any safety requirements or measures associated with the hazards.
SR ID | SRAC ID from the SRAC list.
SR Title | A safety requirement/measure. Look-up to SRAC table.
Demonstration state | An indication of whether or not compliance with the safety requirement has been demonstrated. Look-up to SRAC table.
Assumptions | System assumptions identified during the risk assessment process.
Risk rank after the additional safety requirements
Final likelihood of happening | Likelihood of happening considering that the additional safety requirement is applied. One of Frequent or almost certain; Likely; Possible; Unlikely; or Rare.
Final severity level | Severity level considering that the additional safety requirement is applied. One of Insignificant; Minor; Moderate; Major; Catastrophic.
Final risk ranking | The overall results of ranking the hazard considering that the additional safety requirement is applied. The ranking is calculated automatically.
Other actions | Details (see below) of any actions that have been taken to progress the hazard but which are not concerned with implementing safety measures, for example, actions to confirm assumptions.
Action | A description of the action. | Responsible | The person responsible for completing the action.
Target date | The target date for completion of the action, if not complete. | Status | An indication of whether or not the action has been completed.
Notes | Any other information about the hazard considered useful to the users of the hazard record.
Safety-Related Application Conditions (SRACs)
SRAC ID | A unique identifier for the SRAC. The identifier should not be changed or reused.
SRAC Title | Safety requirement/measure title.
SRAC Description | Safety requirement/measure description. Examples of measures taken to reduce the computed risk: - introduction of a safety or monitoring system; - introduction of design measures; - computational evidence and/or representative testing; - operational measures; - maintenance measures. Analyses made should take into account any limitations, accuracy of the information, and may also include confidence levels on data and sensitivity analysis.
Actor Responsible | The ‘actor’, which will typically be an organisation / person assigned responsibility for managing the hazard. This will be the proposer unless and until transferred to another actor, as set out in clause 1.2.2 of Annex I of the regulation.
Demonstration method | The means by which compliance with the safety requirement has been demonstrated or will be demonstrated, typically, by reference to a test or survey activity.
Demonstration state | An indication of whether or not compliance with the safety requirement has been demonstrated. One of Pending; or Demonstrated.
Demonstration evidence | References to any documents, such as test reports, containing further information about the demonstration of this safety requirement.

## Cover
Hazard Log
IDENTIFICATION
PROJECT NAME: |  | Certification of Critical Systems
PROJECT CODE: |  | CECRIS
VCS REPOSITORY:
REFERENCE:
ROLE: | NAME: |  | SIGNATURE: |  | DATE:
Prepared by | Francisco Moreira |  |  |  | 2016-01-05
Verified by
Approved by
Purpose
The hazard log is used for hazard management throughout the project lifecycle. The hazard log is an ongoing tool used to manage hazards by: a) logging all identified hazards; b) recording the identification and development of appropriate controls; c) documenting defined safety requirements; d) providing traceability to supporting evidence; e) recording changes to hazard records or controls along with any justification for the change.
VERSION | DATE | DESCRIPTION |  | AUTHOR
- | 2016-01-05 | First version |  | Francisco Moreira
-
©2015 Copyright CRITICAL Software S.A. All Rights Reserved.
No commercial use of this template is permitted without previous request sent to cecris@criticalsoftware.com.
This work has been partially supported by the European Project FP7-2012-324334-CECRIS (CErtification of CRItical Systems) Grant Agreement no.: 324334 IAPP Marie Curie Action, 7th Framework Program http://www.cecris-project.eu

## Hazard Log
|  |  | Project: | Certification of Critical Systems | [19 empty] | Last edited on: | <date>
[24 empty] | Last edited by: | <person name>
Hazard Log
[7 empty] | Risk rank | [7 empty] | Additional safety measure |  |  |  | Risk rank after the additional safety requirements |  |  | Actions
Hazard identifier | Hazard title | Hazard descripton | Hazard consequence | Hazard cause(s) | Origin | Existing safety measures | Broadly acceptable | Justification if broadly acceptable | Likelihood of happening | Severity level | Risk ranking | State | Risk evaluation principle(s) | Risk evaluation documents | SR ID | SR Title | Demonstration state | Assumptions | Final likelihood of happening | Final severity level | Final risk ranking | Action | Responsible | Target date | Status | Notes
HZ-01 | First hazard | [7 empty] | Frequent or almost certain | Minor | Undesirable | Transferred |  |  | 1 | asd | Pending |  | Frequent or almost certain | Minor | Undesirable |  |  | 2016-01-01 | Pending input
HZ-02 | Second hazard | [7 empty] | Frequent or almost certain | Major | Intolerable |  |  |  | 2 | ccccc | Demonstrated
[9 empty] | Possible | Moderate | Tolerable

## SRAC
|  | Project: | Certification of Critical Systems |  | Last edited on: | <date>
[5 empty] | Last edited by: | <person name>
Safety-Related Application Conditions (SRACs)
SRAC ID | SRAC Title | SRAC Description | Actor Responsible | Demonstration method | Demonstration state | Demonstration evidence
1 | asd |  |  |  | Pending
2 | ccccc |  |  |  | Demonstrated

## Dashboard
Risk map before additional measures | [7 empty] | Risk map AFTER additional measures
Frequency / Consequence |  | Insignificant | Minor | Moderate | Major | Catastrophic |  | Frequency / Consequence |  | Insignificant | Minor | Moderate | Major | Catastrophic
|  | 1 | 2 | 3 | 4 | 5 |  |  |  | 1 | 2 | 3 | 4 | 5
Frequent or almost certain | 5 | 0 | 1 | 0 | 1 | 0 | 2 | Frequent or almost certain | 5 | 0 | 1 | 0 | 0 | 0 | 1
Likely | 4 | 0 | 0 | 0 | 0 | 0 | 0 | Likely | 4 | 0 | 0 | 0 | 0 | 0 | 0
Possible | 3 | 0 | 0 | 1 | 0 | 0 | 1 | Possible | 3 | 0 | 0 | 0 | 0 | 0 | 0
Unlikely | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Unlikely | 2 | 0 | 0 | 0 | 0 | 0 | 0
Rare | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Rare | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 1 | 1 | 1 | 0 | 3 |  |  | 0 | 1 | 0 | 0 | 0 | 1
Total number of hazards: | 2

## Configuration
Hazard state
Open | The initial status assigned immediately after a hazard has been identified.
Controlled | he risk evaluation process has been completed and safety requirements have been established which are sufficient to control risk to an acceptable level. | Broadly | Likelihood | Consequence | Risk ranking matrix
Closed | The potential hazards have been determined not to be an actual hazard or to be wholly contained within another hazard so no further action is necessary. | Yes | Frequent or almost certain | Insignificant | Frequency / Consequence |  | Insignificant | Minor | Moderate | Major | Catastrophic
Transferred | The hazard has been transferred to another actor who now takes the lead in delivering the associated safety requirements for controlling the risk of the hazard. The proposer retains responsibility for managing the hazard. | No | Likely | Minor |  |  | 1 | 2 | 3 | 4 | 5
Cancelled | Compliance with all safety requirements related to the hazard has been demonstrated and any other actions associated with the hazard have been satisfactorily completed and so no further action is required. |  | Possible | Moderate | Frequent or almost certain | 5 | Tolerable | Undesirable | Intolerable | Intolerable | Intolerable
|  |  | Unlikely | Major | Likely | 4 | Tolerable | Tolerable | Undesirable | Intolerable | Intolerable
|  |  | Rare | Catastrophic | Possible | 3 | Negligible | Tolerable | Tolerable | Undesirable | Intolerable
[5 empty] | Unlikely | 2 | Negligible | Negligible | Tolerable | Tolerable | Undesirable
[5 empty] | Rare | 1 | Negligible | Negligible | Negligible | Tolerable | Tolerable
|  | Action States | SRAC States
|  | Open | Pending
|  | Closed | Demonstrated
Pending input